## Amazon-like
Amazon-like Website
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS
Amazon-Like | David D. | 2020-09-27 | Not defined |  | 90%
At risk or needs re-evaluation? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Create Homepage/Website Base (HTML and CSS) |  |  | 8 | 2020-10-01 | 2020-10-04 | 3 | Complete
| Adding sidebar(s) Menu and Product Page (No JavaScript) |  |  | 5 | 2020-10-04 | 2020-10-05 | 1 | Complete
| Add JavaScript to Sidebar(s) Menu and Product Page |  |  | 10 | 2020-10-05 | 2020-10-06 | 1 | Complete
| Build UI Elements |  |  | 5 | 2020-10-06 | 2020-10-07 | 1 | Complete
| Create Shopping Cart feature |  |  | 10 | 2020-10-07 | 2020-10-09 | 2 | Complete
| Web Server Creation |  |  | 10 | 2020-10-09 | 2020-10-12 | 3 | Complete
| Manage DataBase |  |  | 10 | 2020-10-12 | 2020-10-14 | 2 | Complete
| SQL Products Logic |  |  | 10 | 2020-10-14 | 2020-10-17 | 3 | Complete
| Registration and Sign-In Page |  |  | 8 | 2020-10-17 | 2020-10-19 | 2 | Complete
| Checkout Form (Cart) |  |  | 8 | 2020-10-19 | 2020-10-21 | 2 | Complete
| Order Creation and Management |  |  | 8 | 2020-10-21 | 2020-10-24 | 3 | Complete
| Search and Sort Products Logic |  |  | 8 | 2020-10-24 | 2020-10-26 | 2 | Not Started | Still under development.

## Sheet1
Complete
In Progress
Overdue
Not Started